## Application Summary
Application and Certificate for Payment (G702-style)
A working template modeled on the standard G702/G703 format — not an official AIA document. Free from SitewideOps (sitewideops.com).
Yellow cells are yours to fill in; every other number computes from the Continuation Sheet and the rates below.
To (Owner): | Example Owner LLC | Project: | Example Office Park — Bldg B
From (Contractor): | Your Company, Inc. | Project / Contract No.: | PRJ-2026-014
Application No.: | 3 | Period To: | 2026-08-31
Contract Date: | 2026-01-15 | Distribution: | Owner / Architect / Contractor
Retainage rate — completed work | 10%
Retainage rate — stored materials | 10%
1. Original Contract Sum |  |  | 500000
2. Net Change by Change Orders
3. Contract Sum to Date (Line 1 ± 2)
4. Total Completed & Stored to Date (Continuation Sheet)
5a. Retainage on Completed Work (rate × work completed)
5b. Retainage on Stored Materials (rate × stored)
5. Total Retainage (5a + 5b)
6. Total Earned Less Retainage (Line 4 − Line 5)
7. Less Previous Certificates for Payment |  |  | 40500
8. CURRENT PAYMENT DUE (Line 6 − Line 7)
9. Balance to Finish, Including Retainage (Line 3 − Line 6)
Change Order Summary
|  | Additions | Deductions
Total changes approved in previous months |  | 0 | 0
Total approved this month |  | 0 | 0
TOTALS
Net Change by Change Orders (feeds Line 2)

## Continuation Sheet
Continuation Sheet (G703-style) — Schedule of Values Detail
One row per schedule-of-values line. Totals tie to the Application Summary sheet by formula.
Yellow cells are yours to fill in; every other number computes. Row 6 is a worked example — replace it with your own lines.
Item No. | Description of Work | Scheduled Value | Work Completed — Previous Applications | Work Completed — This Period | Materials Presently Stored | Total Completed & Stored to Date | % | Balance to Finish | Retainage
1 | Roof membrane system (example) | 120000 | 45000 | 30000 | 10000
TOTALS